## Action Plan G1Y1
GOAL 1: ACTION PLAN FOR YEAR 1
Goal #1: All children, birth through age five, will have access to adequate and equitably funded quality early care and education programs that meet the diverse needs of families.
This action plan addresses strategies/activities that improve the availability, affordability, and quality of early childhood care and education services by creating and maintaining an effective State structure that supports the need of families for full-day year-round care, facilitates transitions to public schools, increases professional and career development opportunities for child care providers, and builds family, community and societal demand for high-quality early care and education services for all children.
Objective | Activity | Timeframe (by:) | Responsible | Measure of Success
1.1- The Early Childhood Advisory Council will carry out a coordinating and information-sharing role in working with local early care and education service providers and community partners in assessing the availability of high-quality early care and education. | 1.1.1- Identify high quality early care and education service providers and community partners by region. | December, 2010 | Council staff and data consultant, MSDE Division of Early Childhood Development (DECD) | Definition of “ high quality.”
Design of a database based on established criteria, i.e., accredited programs, QRIS level four or five stars.
| 1.1.2- Review a Statewide needs assessment to assess the availability of high-quality early care and education. | February, 2011 | Council staff and data consultant, Governor’s Office for Children (GOC), Maryland Family Network (MFN), DECD | Completed review and analysis of current needs assessments and plan revisions, if needed.
| 1.1.3- Track progress toward the Council’s goals by establishing and monitoring accountability for results through a set of performance management systems, in collaboration with Children’s Cabinet agencies. | March, 2011 and subsequent years. | Council staff and data consultant, DECD, GOC | Completed report in accordance with protocols of the Maryland Longitudinal Data System and annual School Readiness data.
Evaluation of agency systems data compatibility and sharing permissions.
| 1.1.4 – Convene a minimum of three Advisory Council meetings and establish working subcommittees. | June, 2011 | Council Staff, DECD | Completed report with accomplishments, challenges, and plan revisions.
1.2 - Maintain the viability of high-quality early care and education provided by non-public programs while also expanding pre-k. | 1.2.1- Monitor the impact of public pre-kindergarten, by jurisdiction, on Head Start and the private child care sector. | December, 2010 | Council staff and data consultant, MFN. DECD | Data on current child care program closings and increases in the number of pre-k programs.
Interviews with affected providers.
| 1.2.2- Support workforce skills and competencies through expansion of professional development and career opportunities in the field of early childhood education including child health, mental health, and targeted disabilities training. | March, 2011 | Council Staff, MSDE Division of Special Education and Early Intervention (DSP/EI), Department of Health and Mental Hygiene Mental Health Administration (DHMH,/MHA), DECD | 2.1.2 - Statewide survey results.
Current participation data: Credentialing, Career and Professional Development Fund, Early Childhood Mental Health Certificate.
Evaluation of available training and education opportunities and determination of needs.
1.3- Work with early care and education providers on partnership and transition strategies for all children moving from early childhood programs to public schools. | 1.3.1- Promote formal agreements between public schools and Head Start programs regarding transitions for all children and their families, including children with disabilities and English Language Learners. | December, 2010 | Council staff, DECD, DSE/EI, MHSA | Copies of current signed agreements.
Maryland Model for School Readiness (MMSR) 2010 Achievement Results for children who attended Head Start programs.
| 1.3.2 -Promote formal agreements between public schools and child care programs regarding transitions for all children and their families, including children with disabilities and English Language Learners. | December, 2010 | Council staff, DECD, DSE/EI, MSCCA, MFCCA | Copies of draft agreements.
MMSR 2010 Achievement Results for children who attended child care programs.
| 1.3.3 - Support the family choice fo the Extended IFSP Option for eligible children beyond age 3. | On - going | DECD, DSE/EI | Number of families choosing to continue early intervention services through an IFSP beyond the age of 3.
Number of families choosing to receive special education and related services through an IEP beyond the age of 3.
1.4 - Build family, community and societal demand for high-quality early care and education services for all children. | 1.4.1- Monitor the development of a statewide Quality Rating and Improvement System (QRIS). | January, 2011 | Council staff, data consultant, DECD, MSCCA, MHSA, MFCCA | QRIS completed plan and guide. Established pilots by DECD.
Established pilots
| 1.4.2 - Support the increase in the number of accredited programs and credentialed providers. | May, 2011 | Council Staff, DECD | 5% increase in number of programs/providers participating.
| 1.4.3 -Promote cultural sensitivity and outreach for minority and immigrant children through professional development. | April, 2011 | Council staff, DECD | MMSR Achievement Results 2010 for Hispanic children.
Professional development modules for providers on cultural sensitivity.
1.5- Analyze, assess and develop structure for affordable high quality programs that address families’ needs, and change structures with the goal of developing truly “seamless” services. | 1.5.1 - Link and enhance websites and locations where families can learn of available early childhood resources. | February, 2011 and subsequent years | Council staff, GOC, DECD, DHMH/MHA, MFN, Council staff | Enhanced consumer education portals.
| 1.5.2 - Support increases in early childhood programs that are inculsive, high quality, and accessible to young children with disabilities and their families. | Ongoing | Council Staff, data consultant, DECD, DSE/EI | Satisfaction survey of families employing the IFSP option.

## Action Plan - G1Y2
GOAL 1: ACTION PLAN FOR YEAR 2
Goal #1: All children, birth through age five will have access to adequate and equitably funded quality early care and education programs that meet the diverse needs of families
This action plan addresses strategies/activities that improve the availability, affordability, and quality of early childhood care and education services by creating and maintaining an effective State structure that supports the need of families for full - day, year - round care, facilitates transitions to public schools, increases professional and career development opportunities for child care providers, and builds family, community and societal demand for high - quality early care and education services for all children.
OBJECTIVE | ACTIVITY | TIMEFRAME: (BY:) | RESPONSIBLE | MEASURE OF SUCCESS
1.1 - The Early Childhood Advisory Council will carry out a coordinating and information sharing role in working with local early care and education councils and community partners in identifying and assessing the availability of high - quality early care and education. | 1.1.1 - Identify high quality early care and education service providers and community partners by region. | August, 2012 | MSDE Division of Early Childhood Development (DECD), Council Staff and Data Consultant | Established database of accredited programs.
| 1.1.1.1 -Create linkages between early learning and development programs with potential community partners. | August, 2012 | DECD, Maryland Family Network (MFN), Council Staff | Comprehensive list of community partners of accredited programs made available to providers.
| 1.1.1.2 -Ensure access to effective practices of quality early care and education programs. | February, 2012 | DECD, Council Staff | Compilation of best practices identified by accreditation and QRIS standards
| 1.1.2 - Review information on the availability of high-quality early care and education. | August, 2012 | DECD, GOC, MFN, Council Staff and Data Consultant | Review, analyze and plan revisions if indicated.
| 1.1.2.1 - Using the information from 1.1.2 and other data to identify under resourced target areas to increase high quality services. | August, 2012 | DECD, MFN, MSCCA, MHSA, MSFCCA, Council Staff, Data Consultant | Develop a baseline number of information and orientation sessions on accreditation and Maryland EXCELS in the targeted area.
| 1.1.2.2 - Increase awareness of the benefits of high quality early care and education services. | August, 2012 | DECD, Ready At Five, MFN, Council Staff, Data Consultant | Assess and coordinate existing quality early childhood services awareness information and campaigns.
| 1.1.3 - Track progress toward the Council's goals by collaborating with an outside evaluator for results through a set of performance management systems, in collaboration with Children's Cabinet agencies. | July, 2012 | DECD, Council Staff and Data Consultant | Annual report on results - based accountability evidencing a 90% compliance rate.
Evaluation reports document completion of all activities and 90% compliance rate with all goals and objectives as stated.
| 1.1.4 - Convene a minimum of three Advisory Council meetings and subcommittee meetings, as determined. | Feb, May, Aug 2012 | DECD, Council Staff | Completed second annual report with accomplishments, challenges, and plan revisions.
1.2 – Maintain the viability of high-quality early care and education provided by non-public programs while also expanding pre-k. | 1.2.1- Monitor the impact of public pre-kindergarten, by jurisdiction, on Head Start and the private child care sector | August, 2012 | DECD, MFN. MSCCA, MHSA, MSFCCA, Council staff and data consultant | Analysis of updated data and survey results with plan revisions when determined necessary
| 1.2.1.1-Assist early care and education providers to increase enrollment of 4-year olds by supporting local partnerships with other early childhood partners, including LEAs. | August, 2012 | DECD, Council Staff and data consultant | Improvement in collaboration and enrollment for affected providers through local partnerships
| 1.2.2 -Support workforce skills and competencies through expansion of professional development and career opportunities in the field of early childhood education including child health, mental health, and targeted disabilities training | August, 2012 | DSE/EIS, DHMH,/MHA, DECD, ECMHSC, Consortium of Early Childhood Faculty in Two and Four-Year Colleges, Council staff | A 5% increase over year one in the number of credentialing and Career and Professional Development Fund participants
A 5% increase in the number of articulation agreements over year one with higher education institutions to participate in the credentialing program.
A 5% increase over year one in the number of early childhood training and education opportunities based on the year one evaluation
| 1.2.2.1 – Support outreach to early care and education providers on early care and education professional development and career opportunities | March, 2012 | DECD, Consortium of two and four-year colleges, professional development organizations | 5% increase in two and four-year colleges participating in Career and Professional Development Fund programs over year one.
5% increase in professional development offerings included on the Statewide Clearinghouse Calendar based on identified training needs over year one
GOAL 1 : ACTION PLAN FOR YEAR 2
Goal #1: All children, birth through age five will have access to adequate and equitably funded quality early care and education programs that meet the diverse needs of families
This action plan addresses strategies/activities that improve the availability, affordability, and quality of early childhood care and education services by creating and maintaining an effective State structure that supports the need of families for full - day, year - round care, facilitates transitions to public schools, increases professional and career development opportunities for child care providers, and builds family, community and societal demand for high - quality early care and education services for all children.
OBJECTIVE | ACTIVITY | TIMEFRAME: (BY:) | RESPONSIBLE | MEASURE OF SUCCESS
1.3- Work with early care and education providers on partnership and transition strategies for all children moving from early childhood programs to public schools. | 1.3.1- Promote formal agreements between local education agencies and Head Start programs regarding transitions for all children and their families, including children with disabilities and English Language Learners. | August, 2012 and ongoing | Council staff, DECD, DSE/EIS, MHSA | Renewed agreements with increased areas of collaboration over year one.
A 2% increase in MMSR Achievement Results for Head Start children over previous year.
| 1.3.2- Promote formal agreements between local education agencies and child care programs regarding transitions for all children and their families, including children with disabilities and English Language Learners. | August, 2012 and ongoing | Council staff, DECD, DSE/EIS, MSCCA, MSFCCA | Copies of signed State and local agreements.
A 2% increase in MMSR Achievement Results for child care over previous year.
| 1.3.3 - Support the family choice of the Extended IFSP Option for eligible children beyond age 3. | Ongoing | DECD, DSE/EIS | Increase in the number of families choosing the Extended IFSP Option, improved child outcomes and family satisfaction based on survey results.
1.4 - Increase the access to families for high quality early care and education services. | 1.4.1- Monitor the pilot of a statewide Quality Rating and Improvement System (QRIS). | August, 2012 and ongoing | Council staff, data consultant, DECD, MSCCA, MHSA, MSFCCA | Completed QRIS pilot assessment/evaluation.
Roll-out completed for all early care and education programs.
| 1.4.1.1 –Increase awareness of the benefits of participating in QRIS. | August, 2012 and ongoing | Council Staff, DECD | Information on QRIS distributed by hard copy and available on the web.
Survey of providers on knowledge of QRIS.
| 1.4.2- Support the expansion of the number of accredited programs and credentialed providers. | July, 2012 | Council Staff, DECD, MFN | Established mechanisms that link mentors and technical assistance to providers.
A 5% increase over year one in the number of accredited providers and in the number of providers participating in credentialing.

## Action Plan - G1Y3
GOAL 1: ACTION PLAN FOR YEAR 3
Goal #1: All children, birth through age five, will have access to adequate and equitably funded quality early care and education programs that meet the diverse needs of families.
This action plan addresses strategies/activities that improve the availability, affordability, and quality of early childhood care and education services by creating and maintaining an effective State structure that supports the need of families for full-day year-round care, facilitates transitions to public schools, increases professional and career development opportunities for child care providers, and builds family, community and societal demand for high-quality early care and education services for all children.
OBJECTIVE | ACTIVITY | TIMEFRAME (BY): | RESPONSIBLE | MEASURE OF SUCCESS
1.1- The Early Childhood Advisory Council will carry out a coordinating and information-sharing role in working with local early care and education service providers and community partners in assessing the availability of high-quality early care and education. | 1.1.1- Identify high quality early care and education service providers and community partners by region. | October, 2012 | DECD, Council staff and data consultant | Updated database of accredited and QRIS four and five star programs
| 1.1.1.1- Assist service providers connect with potential community partners. | December, 2012 | DECD, MFN, Council staff | A 3% increase over year 2 in the number of accreditation applicants.
A 5% increase in number of community partnerships by accredited programs over year 2
| 1.1.1.2 -Develop and disseminate best practices of quality early care and education programs. | March, 2013 | DECD, Council staff | Share effective practices with providers and the training/technical assistance community.
Use of newsletters, such as partners, for dissemination of best practices.
| 1.1.2- Update needs assessment on the availability of high-quality early care and education. | February, 2013 | DECD, GOC, MFN, Council staff, data consultant | Updated needs assessment, analysis, and plan revisions where indicated.
| 1.1.2.1 – Identify areas with minimal availability to increase quality services | January, 2013 | DECD, MFN | 3% increase in the number of accreditation applications and QRIS participants in targeted areas over year two.
Increase of 5% over year one in the number of provider applications for accreditation or QRIS.
| 1.1.2.2- Increase awareness of the benefits of high quality early care and education services. | February, 2013 | DECD, MFN, Council staff, data consultant. | Knowledge of parents and the public of quality early childhood services assessed through surveys.
Increase of 5% in child enrollment in accredited programs.
| 1.1.3- Track progress toward the Council’s goals by establishing and monitoring accountability for results through a set of performance management systems, in collaboration with Children’s Cabinet agencies. | January, 2013 | DECD, GOC, Council staff | Annual report on results-based accountability system with progress meeting all performance indicators.
| 1.1.4 – Convene a minimum of three Advisory Council meetings and subcommittee meetings. | June, 2013 | DECD, Council staff | Completed final report with accomplishments, challenges, and plan revisions.
1.2 – Maintain the viability of high-quality early care and education provided by non-public programs while also expanding pre-k. | 1.2.1- Monitor the impact of public pre-kindergarten, by jurisdiction, on Head Start and the private child care sector. | October, 2012 | DECD, MFN, Council Staff, data consultant | Analysis of updated data survey results and monitoring of plan revisions.
| 1.2.2- Assist early care and education providers with diminished enrollment of 4-year olds develop plans and mechanisms to increase overall enrollment. | January, 2013 | DECD, MFN, Council Staff, data consultant | Increased number of community programs and public school partnerships.
Increased enrollment for affected providers based on individual plans.
| 1.2.2.1 - Support workforce skills and competencies through expansion of professional development and career opportunities in the field of early childhood education including child health, mental health, and targeted disabilities training. | March, 2013 | DSP/EI, DHMH,/MHA, DECD, ECMHSC | Increase of 5% in the number of participants in credentialing and in the Career and Professional Development Fund programs over year two.
5% increase in articulation agreements with higher education institutions over year two.
| 1.2.2.2 – Conduct outreach to early care and education providers on early care and education professional development and career opportunities. | May, 2013 | DECD | 5% increase in professional development offerings included on the Statewide Clearinghouse Calendar based on identified training needs over year two.
1.3- Work with early care and education providers on partnership and transition strategies for all children moving from early childhood programs to public schools. | 1.3.1 - Promote formal agreements between local education agencies and Head Start programs regarding transitions for all children and their families, including children with disabilities and English Language Learners. | January, 2013 | DECD, DPE/EI, MHSA, Council staff | Renewed agreements with increased areas of collaboration over year two.
2% increase in MMSR Head Start Achievement Results over previous year for children attending Head Start.
Continuing schedule of renewals and facilitation.
| 1.3.2 -Promote formal agreements between local education agencies and child care programs regarding transitions for all children and their families, including children with disabilities and English Language Learners. | April, 2013 | DECD, DPE/EI, MSCCA, MFCCA, Council staff | Copies of current signed State and local agreements.
Schedule of renewals and facilitation.
2% increase in Maryland Model for School Readiness (MMSR) Achievement Results for child care over year two results.
| 1.3.3 - Support the family choice of the Extended IFSP option for eligible children beyond age 3. | Ongoing | DECD, DSE/EI | Measure family training and support, family/parent satisfaction by survey.
1.4- Build family, community and societal demand for high-quality early care and education services for all children. | 1.4.1 -Monitor a statewide Quality Rating and Improvement System (QRIS). | February, 2013 | DECD, Council staff, data consultant | Completed roll-out for all early care and education programs.
| 1.4.1.1–Increase awareness of the benefits of participating in QRIS. | February, 2013 | DECD, Council Staff | Periodic random survey of providers on knowledge of QRIS.
5% increased number of QRIS participants over year two.
| 1.4.2-Support the expansion of accredited programs and credentialed providers. | March, 2013 | DECD, MFN, Council Staff | Additional 5% increase in the number of accredited providers and in the number of providers participating in credentialing.
| 1.4.3 -Promote cultural sensitivity and outreach for minority and immigrant children. | April, 2013 | DECD, Council Staff | Increase in the number of participants in new training modules.
2% increase in MMSR Achievement Results for Hispanic children over year two results.

## Action Plan G2Y1
GOAL 2: ACTION PLAN FOR YEAR 1
Goal #2: Families of all young children will have access to the resources needed to be their child’s first teacher.
OBJECTIVE | ACTIVITY | TIMEFRAME: (BY:) | RESPONSIBLE | MEASURE OF SUCCESS
2.1 Convene Community Listening forums to reflect the cultural diversity of Maryland's communities to give families a voice in determining the content and av ilabiltiy of community-based programs to support their interests and needs | 2.1.1 Identify local contacts in jurisdictions to secure broad based participation at Listening Forums. Target audiences include low-income families; teen moms, Foster Care families and families with special needs and non English-speaking children. | November, 2010 | Council staff, DECD, Consultant/Facilitator | Roster of local contacts Number of events conducted in each jurisdiction
| 2.1.2 Develop a forum template, program and evaluation tool. | December, 2010 | Council staff, DECD, consultant/facilitator | Forum template, program and evaluation developed
| 2.1.3 Convene local listening forums targeting families, representing different constituencies, early care and education stakeholders and service providers, including the health community. | January, 2011 | Council Staff, DECD | Analysis of comments.
| 2.1.4 Council staff will analyze the information and create a basis for incorporating new action items into its Action Plan. | March, 2011 | Council staff, DECD | Report of forum results; implications for public policy and legislation. Widely disseminate findings.
| 2.1.5 Forum results and Council’s Action Plan will be widely disseminated: face-to-face, on line and in print. | July, 2011
2.2 Monitor the development of community-based partnerships throughout Maryland that focus on early childhood and health and reflect the diversity of Maryland families’ needs. | 2.2.1 - Promote coordinated community networks that embrace families’ needs articulated through and at the community Listening Forums. Networks will provide culturally and linguistically sensitive information and resources to families on child development, quality early care and education settings, developmental disabilities, health, parenting, and resources. | July, 2011 | Council staff, DECD,State Interagency Councils, Departments of Social Services, including foster care staff, DSP/EI | Evaluation Components: ---Increased number of families who have access to information on child development, parenting and health services and use the information at home to support their children's learning as reported through surveys, interviews, and anecdotal reports. ---Increased number of families who use the library, museums, etc. with their children and participate in Learning Parties, as reported through attendance and performance data. Established communication strategies and guidance for child care providers.
| 2.2.2 Use the Office of Child Care’s Healthy Beginnings: Supporting Development and Learning for Infants Through Age 3 documents to disseminate information about milestones and appropriate interventions and activities that support families and caregivers needs. | November, 2010 | OCC/DECD
| 2.2.3 - Improve the accessibility of resources to parents, regardless of language, culture, or disability. | Ongoing | DECD, DEC/EI | Increase in number of families requesting information on child development and health from MSDE, MFN, and RAF
2.3 - Develop a statewide strategy that promotes successful transitions among and between programs for young children and their families. | 2.3.1 - Ensure the establishment of an ECAC Transition sub-committee of ECAC members and additional stakeholders (ece community, LEA’s, families, health practitioners, non profits, State agencies, and stakeholders]. | May, 2011 | DECD, Council staff, GOC | An expanded Maryland Longitudinal Data System to track enrollment information from early childhood to school.
| 2.3.2. Apply a data management strategy and system to improve transitions between early care and education programs and public schools. |  |  |  | ]
| 2.3.3 - Identify and catalogue successful and effective transition practices and policies within and outside Maryland. | August, 2011 | Council staff, DECD, DSE/EI, DHMH | Transition practices disseminated via websites and other methods.
Increased number of schools and early care and education programs implementing transition plans in partnership with families.
| 2.3.4 - Families choosing the extended IFSP option will continue to receive service coordination and offering if needed family training and support. | Ongoing | DECD, DSE/EI | Parent satisfaction results
2.4 Create a home visiting infrastructure that serves all Maryland children birth to 3 | 2.4.1 Develop a strategy to reorganize the home visiting structure in Maryland. | August, 2011 | Council staff, DECD, DSE/EI, DHMH, GOC | Completed plan for a home visiting consortium.
| 2.4.2 Identify funding sources that support a comprehensive home visiting strategy to reach vulnerable populations (homeless, foster care, low income, English language learner young children and children of teen mothers.) |  |  | Infant and Toddler specialists are available through the Child Care Resource Centers for technical assistance to child care programs.
Support home visiting application for evidence -based home visiting.

## Action Plan G2Y2
GOAL 2: ACTION PLAN FOR YEAR 2
Goal #2: Families of all young children will have access to the resources needed to be their child’s first teacher.
OBJECTIVE | ACTIVITY | TIMEFRAME: (BY:) | RESPONSIBLE | MEASURE OF SUCCESS
2.1 The council members of this goal group will assume a leadership and planning role for the Family Engagement Coalition as determined by the Race to the Top Early Learning Challenge Grant. | 2.1.1 Work with the Family Engagement Coalition to gather data, information and research to develop a statewide family survey to inform the early childhood community of the needs of young children and their families. | August, 2012 | Council staff, DECD, GOC | A completed family survey with a distribution and analysis plan. A compliled famliy contact list for dissemination.
2.2 Create and expand community-based partnerships throughout Maryland that focus on early childhood and reflect the diversity of Maryland families’ needs. | 2.2.1 Work with the local Early Childhood Advisory Councils as determined by the Race to the Top ELCG as part of the statewide effort to compile and conduct a family survey. | August, 2012 and ongoing | Council Staff, DECD, GOC, DHMH | A completed family survey with a distribution and analysis plan. A compliled famliy contact list for dissemination.
| 2.2.2 Local Councils will participate by providing contact information for early childhood partners in their local jurisdiction to build the survey dissemination list. | 2012-08-01
| 2.2.3 - Improve access to resources for parents regardless of language, culture, or disability through the local Early Childhood Councils. | August, 2012 | Council Staff, DECD, DHMH, GOC, MFN | A completed list of statewide early childhood resources by jurisdiction for dissemination by all 24 local early childhood councils.
2.2.4 Representatives from all 24 local early childhood councils will meet with the ECAC to analyze efforts to connect families to resources.
Annual report includes status and progress of community partnerships
2.3 - Develop a statewide strategy that promotes successful transitions among and between programs for young children and their families, including for children with disabilities. | 2.3.1 Convene a statewide taskforce to identify effective practices and policies for potential implementation on the topic of early childhood transitions. | August, 2012 | Council staff, DECD | Early Childhood Task Force members identified, meeting schedule developed. Outcome report provided on findings.
| 2.3.2 Pilot the identified early childhood transition plan in two jurisdictions | August, 2012 and ongoing | Council staff, data consultant,MSDE, DECD | Analyze results based on formalized agreements with all early childhood community partners and the local school system and family satisfaction results.
| 2.3.3 - Families choosing the extended IFSP option will continue to receive service coordination and offering if needed family training and support. | Ongoing | DECD, DSE/EIS | Parent satisfaction results
2.4 - Develop a strategy to ensure that evidence-based home visiting is a part of Maryland's aligned early childhood system and its Race to the Top effort in all Maryland jurisdictions | 2.4.1 - Coordinate activities and increase positive effects of high quality home visiting programs for families through the home visiting consortium. | August, 2012 and ongoing | Council Staff, DECD, DSE/EIS, GOC | Recommendations of Consortium presented to ECAC
| 2.4.2 - Link the evidence based home visiting programs with family and early childhood services statewide | August, 2012 | Same as Above | A completed list of statewide early childhood resources by jurisdiction that includes home visiting families and resources
0

## Action Plan G2Y3
GOAL 2: ACTION PLAN FOR YEAR 3
Goal #2: Families of all young children will have access to the resources needed to be their child’s first teacher.
OBJECTIVE | ACTIVITY | TIMEFRAME: (BY:) | RESPONSIBLE | MEASURE OF SUCCESS
2.1 Convene Community Listening forums to reflect the cultural diversity of Maryland's communities to give families a voice in determining the content and availability of community-based programs to support their interests and needs. | 2.1.1 - Promote the use of existing and create additional information on child development, early care and education, and health (publications, brochures, etc) and face-to-face opportunities (Learning Parties, multiple language library Story Hours) that are linguistically and culturally sensitive, accessible, comfortable for parents, and a result of the forums. | October, 2012 | Council staff, DECD, DHMH | Number of publications distributed; distribution points; number of face-to-face convening; new publications developed; survey to determine information gained; greater access to services
2.2. Create and expand community-based partnerships throughout Maryland that focus on early childhood and health and reflect the diversity of Maryland families’ needs. | 2.2.1 -Ensure that Maryland communities that have identified Children Entering School Ready to Learn (CESRTL) as a priority have community partnerships, early education and care and health services and meet the needs of families. | April, 2013 | Council Staff, DECD, DHMH, GOC, Governor's Children's Cabinet | Final Report on progress and outcomes during 3-year period, verifying that all Maryland communities and jurisdictions have community partnerships to create seamless early childhood and health services that meet the needs of families.
| 2.2.2 Encourage communities to adopt CESRTL as priority | March, 2013 | Council staff, data consultant, DECD, GOC, DHMH
2.3. Develop a statewide strategy that promotes successful transitions among and between programs for young children and their families, including for children with disabilities. | 2.3.1 - Facilitate comprehensive agreements between Local Education Agencies and child serving agencies. | December, 2012 | Council staff, DECD, DSP/EI | Comprehensive agreements are in place in all communities, involving school systems and community-based programs that include transition policies, sharing enrollment data, and family engagement 50% of Maryland child care and Head Start programs participate in the Maryland Longitudinal Data System.
January, 2013
| 2.3.2 - Families choosing the extended IFSP option will continue to receive service coordination and offering if needed family training and support. | Ongoing | DECD, DSE/EI | Parent satisfaction results
2-4 - Implement a strategy to reorganize the home visiting structure in Maryland | 2.4.1 - Develop or align standards for quality home visiting programs | February, 2013 | Council Staff, DECD, GOC, DPE/EI | Completed standards.
| 2.4.2 - Disseminate standards to home visiting programs and provide training guide for the standards | August, 2013 | Same as above | Completed training guide

## Action Plan G3Y1
GOAL#3: ACTION PLAN FOR YEAR 1
Goal #3: Children, birth through age five, will have access to adequate and equitable resources that will enable them to arrive at school with healthy minds and bodies.
This action plan…..
Objective | Activity | Timeframe (By:) | Responsible | Measure of Success
3. 1- The ECAC will utilize existing statewide assessments to define the needs of families and increase knowledge and support to families in need of early childhood mental health and children’s health, including developmental needs. | 3.1.1- Develop a report on results for needs and gaps, including recommendations. | October, 2011 | DHMH- Center for Maternal and Child Health, MSDE Division of Early Childhood Development (DECD), Council staff, data consultant | This 2011 report will serve as the baseline for future needs assessments and gap analyses.
3. 2 - Increase knowledge and support for Maryland’s Social Emotional Foundations of Early Learning (MD-SEFEL) Partnership. | 3.2.1- Support expansion of trainers statewide. | On - going | DECD, DSE/EI, DHMH, SEFEL | 10% of all licensed early childhood programs will have access to MD SEFEL training.
| 3.2.2 - Align MD - SEFEL with PBIS. |  | Council Staff
3.3- Recommend legislation to establish a Task Force on Child Health and School Readiness to study and determine regulations, policies, and practices supporting early childhood mental health and health impacting school readiness. | 3.3.1- Introduce legislation to establish a task force. | December, 2010 | Children’s Cabinet, Governor’s Office for Children (GOC) and Joint Committee on Children, Youth and Families, MSDE, Council Staff | Proposed legislation will be drafted, reviewed, and approved.
| 3.3.2- Establish Task Force and issue report. | December, 2011 | ECAC, Children’s Cabinet, GOC, MSDE, DHMH, and Council staff | legislation will describe required task force membership and will include Children’s Cabinet agencies, families and advocates.
3.4. – Provide professional support for the Early Childhood Mental Health Consultation Project in every jurisdiction and improve the coordination with the public schools’ early intervention and Special Education services . | 3.4.1- Conduct a management review of the current ECMH services and its coordination with existing early intervention and special education services | June, 2011 | MSDE, DHMH, Council staff, data consultant | June 2011 baseline will be established
| 3.4.2- Support continuation of post-master certification program | June, 2011 | DECD, DHMH, DSE/EI, Council Staff | Training and orientation provided to 10% of ECMH behavior specialists on the implementation of the ECMH consultation standards.
GOAL#3: ACTION PLAN FOR YEAR 1
Goal #3: Children, birth through age five, will have access to adequate and equitable resources that will enable them to arrive at school with healthy minds and bodies.
This action plan…..
Objective | Activity | Timeframe (by:) | Responsible | Measure of Success
3.5- Extend the Child and Adult Care Food Program to informal child care providers. | 3.5.1- MSDE/ OCC will continue collaboration with the Governor’s Partnership to End Childhood Hunger and identify licensed CC centers and informal child care providers to enroll in CACFP | January, 2011 | Governor’s Partnership to End Childhood Hunger, MSDE/School and Community Programs Nutrition Branch | Increase number of licensed child care centers enrolled in the CACFP 2011: 5% increase (533 centers participating)
3.6- Increase the number of children (including those with special health care needs) accessing health care and oral health care from providers that accept MCHP. | 3.6.1- Support the training of child care staff on an effective family support model that incorporates a health component. | December, 2011 | MSDE (Head Start , Judy Centers), DHMH, family support centers | Implementation of social marketing strategies (dissemination of newsletters, informational materials, links to websites and networking sites) to enhance commitment to medical homes across agencies
5% increase in children using MCHP to access health and oral health care.
| 3.6.2- Support an evaluation of medical home access using Medicaid data. | August, 2011 | DHMH | This 2011 summary will serve as baseline
3.7- Create a “medical home” providing central community health support includes dentists and oral health for children and families. | 3.7.1- Support the definition of components of “medical home”, and establish model program | On - going | DHMH/ Office of Genetics and Children with Special Health Care Needs in collaboration with MD-AAP, pilot ABCD developmental screening project. | 10% increase in provider participation
15% increase in children screened for early intervention services.
10% increase in children referred for early intervention services.

## Action Plan G3Y2
GOAL 3: ACTION PLAN FOR YEAR 2
Goal #3: Children, birth through age five, will have access to adequate and equitable resources that will enable them to arrive at school with healthy minds and bodies.
This action plan …
Objective | Activity | Timeframe (by:) | Responsible | Measure of Success
3. 1- The ECAC will utilize existing statewide data to further define the needs of families to enable them to meet their child's developmental physical and mental health needs. | 3.1.1- Review data on results for needs and gaps, including recommendations | April, 2012 | DHMH, Center for Maternal and Child Health, MSDE Division of Early Childhood Development (DECD), DSE/EIS, Council Staff, data consultant | Gather and analyze 2010 Reperton Report data and 2011 data and write report on analysis. 1. By April 2012 report provided on 2010 data 2. By April 2012, 2011 data collected 3. By July 2012, 2011 data analyzed and report disseminated
3. 2 - Increase knowledge and support for Maryland’s Social Emotional Foundations of Early Learning (MD-SEFEL) Partnership by implementing the pyramid teaching philosophy in all prior early care settings (child care, Head Start, preschool programs). | 3.2.1- Conduct SEFEL Database training to all EL&D programs implementing SEFEL | August, 2012 | Same as above | Quarterly data reports available at the local and state level to analyze the results of SEFEL and for program improvement
| 3.2.2- Expand SEFEL to libraries through staff training | August, 2012 and ongoing | Same as above | Librarians will embed SEFEL within storytime and create a linkage for families to gain access to SEFEL (report data)
| 3.2.3- Build capacity for state trainers and coaches to enhance their skills and knowledge of SEFEL practices. | April, 2012 | Same as above | Completion of Practicum at one of the SEFEL Demo Sites
State trainers will complete 3 day Responsive Training Symposium to increase trainer skills
| 3.2.4- Support SEFEL PBIS collaboration between LEAs and EL&D feeder programs | May, 2012 | Same as above | Agreements between PBIS schools and EL&D programs implementing SEFEL to ensure smooth transitions for children
3.4. – Provide professional support for the Early Childhood Mental Health Consultation Project in every jurisdiction and improve the coordination with the public schools’ early intervention and Special Education services. [2] | 3.4.1- Conduct a management review of the current ECMH services and its coordination with existing special education services | July, 2012 (Annually) | MSDE, DSE/EIS, DHMH, and Council staff | # of jurisdictions having in place mechanisms and processes to coordinate services among ECMHC, the early intervention system, and special education preschool.
| 3.4.4- Provide professional support through training of ECMH Consultants on the web based Outcomes Monitoring System | December, 2011 and ongoing | DECD and Council Staff | Quarterly data reports will be disseminated to the Council from the Outcomes Monitoring System
3.5- Extend the Child and Adult Care Food Program to an increased number of regulated child care programs. | 3.5.1- MSDE/ OCC will continue collaboration with the Governor’s Partnership to End Childhood Hunger and identify regulated child care providers and informal child care providers to enroll in CACFP. | August, 2012 and ongoing | DECD, DHMH, MSDE/School and Community Programs Nutrition Branch, Council Staff | Increase by 5% the number of regulated child care programs enrolled in the CACFP in 2012: a 5% increase represents 560 centers participating.
3.6 Gather information on the barriers to accessing health care and oral health care (MCHP) from providers that serve young children. | 3.6.1- Support the training of child care staff on an effective family support model that incorporates a health component. | August, 2012 - on-going | MSDE , DHMH, MFN | On-going implementation of social marketing strategies (referenced in Year 1) to enhance commitment to medical homes across agencies; Increased access to quality Family support systems.
| 3.6.3-Convene a stakeholder group that includes dentists and physicians to identify barriers to the delivery of care. | August, 2012 and ongoing | DHMH, Council staff | Completed report with barriers, recommendations and next steps to develop a plan that will increase the number of children accessing health services from MCHP participating providers.

## Action Plan G3Y3
GOAL 3: ACTION PLAN FOR YEAR 3
Goal #3: Children, birth through age five, will have access to adequate and equitable resources that will enable them to arrive at school with healthy minds and bodies.
This action plan …
Objective | Activity | Timeframe (by:) | Responsible | Measure of Success
3. 2 - Increase knowledge and support for Maryland’s Social Emotional Foundations of early Learning (MD-SEFEL) Partnership. | 3.2.1- Support expansion of trainers statewide | February, 2013 | Interagency Planning & Leadership Team for MD SEFEL | By October 2013, 15% reduction in expulsions (from Oct. 2010 baseline.)
| 3.2.2- Support implementation of the pyramid teaching philosophy in all prior early care settings (child care, Head Start, preschool programs). | September, 2013 | MD SEFEL Expert Coach and Cadre of Trainers | 15% increase in early childhood programs implemented statewide.
3.5- Extend the Child and Adult Care Food Program to informal child care providers. | 3.5.1- MSDE/ OCC will continue collaboration with the Governor’s Partnership to End Childhood Hunger and identify licensed child care centers and informal child care providers to enroll in CACFP | January, 2013 | Governor’s Partnership to End Childhood Hunger, MSDE/School and Community Programs Nutrition Branch | 5% increase in the number of licensed child care centers enrolled in the CACFP.
2013: a 5% increase would represent 588 centers participating.
3.6- Increase the number of children (including those with special health care needs) accessing health care and oral health care from providers that accept MCHP. | 3.6.1- Train child care staff on an effective family support model that incorporates a health component. | August, 2013 | MSDE (Head Start , Judy Centers), DHMH, family support centers | Continued and increased implementation of social marketing strategies (referenced Year 1) to enhance commitment to medical homes across agencies; Increased access to quality Family support systems.
| 3.6.3- Support an on-going workgroup of physicians and dentists to develop comprehensive screening and treatment for young children | August, 2013 | Medicaid, DHMH AAP | Increase access for women and children eligible for health insurance.
5% increase in number of children using MCHP to access health and oral health over previous year.
3.7- Create a “medical home” providing central community health support includes dentists and oral health for children and families. | 3.7.1- Support the establishment of a model medical home program | On - going | DHMH/ Office of Genetics and Children with Special Health Care Needs in collaboration with MD-AAP, pilot ABCD developmental screening project. | 10% Increase in provider participation statewide.
5% increase in children screened for early intervention services from previous year.
5% increase in children referred for early intervention services from previous year.